Arm-BCI Copilot — Progress Report

The open-loop copilot does learn from trajectory alone; a loader defect had corrupted the real-data trial set; cleaning the inputs improves the copilot gain

July 29, 2026

# Overview

This report executes the three action items from the 7/27 meeting — data cleaning, training/validation loss diagnostics, and feature-space tuning — and reports one unplanned finding that supersedes the others in importance.

The model is functionally sound. Trained as a plain 8-way target classifier, the per-tick training loss falls well below chance (ln 8 = 2.079) for all six subjects, with validation tracking it. Final-tick target accuracy reaches 57–78% against 12.5% chance. There is decodable target information in the trajectory and the LSTM learns it. The earlier "no recoverable pattern" ceiling was a property of how the copilot was being measured, not a limit of the data.

A loader defect had corrupted the real-data trial set. The production loader concatenated all 22 session CSVs and grouped rows by trial keys that are not unique across session folders. It silently merged 3,030 pairs of distinct trials — with different target labels — into single mixed-target sequences, collapsing 16,197 real trials into 13,167 corrupted ones. Every real-data number reported to date sits on this. The true raw-decoder baseline is 64.0%, not the ~53–55% previously reported. This is now fixed.

Cleaning the inputs helps. Trimming the pre-onset dead ticks and normalizing scale across sessions raises the copilot's open-loop gain from +1.10 to +1.50 pp and halves its across-seed variance (±0.30 → ±0.13).

Feature engineering is not the lever. Every richer feature set tested improves validation loss by less than the seed noise. The current feature set is already near-optimal. The one robust finding: the target signal lives in the decoder's per-tick velocity, not in accumulated cursor position.

# 1. What the 7/27 meeting asked

The meeting set a precondition: the two proposed advancements — closed-loop operation and adding language knowledge to the copilot input — only make sense after verifying that (a) the model does something useful in the open loop, and (b) it does something useful from trajectory information alone. Three concrete items followed:

- Data cleaning — trim the leading zeros from each trial, and normalize the velocity/trajectory scaling that differs across sessions.

- Diagnostics — monitor training and validation loss rather than concluding from evaluation accuracy alone that no pattern is recoverable. If training loss does not decrease, the architecture itself is at fault; establish the model is sound before concluding there is nothing to learn.

- Feature space — tune what we feed the copilot.

All three were completed. Sections 2–6 report them in the order the evidence has to be read.

# 2. What the data actually contains

Both cleaning items were confirmed in the data before any code was changed. Across all 22 session CSVs (16,197 trials, six subjects):

| Issue | Measurement |
| --- | --- |
| Leading dead ticks | Trials average 14 ticks, of which ~5.5 are pre-movement-onset dwell. 100% of trials have ≥2. |
| Per-session scale drift | Same subject, different sessions differ in reach and velocity by up to 2.67× (S04). |

For scale drift the extreme case is S04, whose sessions are not on a comparable scale at all:

| S04 session | mean step (px) | mean final radius (px) |
| --- | --- | --- |
| S04_Typing_S2001 | 8.49 | 127.11 |
| S04_WordTyping_S0001 | 20.90 | 229.51 |
| S04_SentenceTyping_S0001 | 22.62 | 251.07 |

Neither was being handled. The normalization in the pipeline covered only velocity-magnitude mean/std, computed per subject with all sessions pooled — never per session — while cursor position was simply divided by a fixed constant. A 127-px-radius session and a 251-px-radius session therefore presented to the model as different tasks.

The cleaning applied. Leading pre-onset ticks are trimmed, and each session is rescaled by a single scalar mapping its median final radius onto a common reference. Rescaling positions rescales velocity by the same factor, so one scalar fixes both drifts. Both steps are metric-safe: the endpoint metric is direction-only (argmax dot-product), so neither can change a trial's label. This is verified — the raw-decoder accuracy is identical, to the decimal, before and after cleaning.

# 3. A loader defect had corrupted the real-data trial set

While folding the cleaning into the shared data module, the raw-decoder baseline changed depending on how the data was loaded — which should be impossible. The cause is a defect in the production loader, and it is the most consequential finding in this report.

Trials are identified by (subject, session_number, run_number, trial_number, inner_trial_number). Those keys are not unique across session folders: S01's WordTyping and SentenceTyping sessions both contain (session 0, run 1, trial 1, inner 1) — with different target labels, 2 and 6. The loader concatenated all 22 CSVs and then grouped by those keys alone, so it stitched distinct trials into one timestamp-ordered sequence and kept whichever label appeared first.

|  | Before (defective) | After (fixed) |
| --- | --- | --- |
| Trials in the real dataset | 13,167 | 16,197 |
| Colliding key-groups merged | 3,030 | 0 |
| Raw-decoder endpoint accuracy | 55.5% | 64.0% |
| Mean angle error | 33.4° | 22.2° |

Consequence. Every real-data result produced to date — the +1 pp open-loop gain, the training-data composition study, the open-loop ceiling diagnostic, and the probes in the 7/22 report — was computed on a set in which 3,030 pairs of trials had been fused into mixed-target sequences. Those conclusions are not necessarily wrong, but none of them is currently supported by a valid measurement.

The fix. Trajectories now carry their source session, the real dataset is always loaded per session folder rather than concatenated, and the train/test splitter blocks by session folder. Verified after the fix: raw and cleaned loads yield identical trial counts, identical held-out test sets, and identical baselines, with zero train/test leakage.

# 4. The learning diagnostic: the model is functionally sound

This is the gating question the meeting posed. To answer it cleanly the copilot control law and its on-policy training loop were stripped away and the LSTM was trained as a plain 8-way target classifier on trajectory features, logging training and validation cross-entropy every epoch. If training loss will not fall, the architecture is at fault; if training falls but validation does not, the problem is overfitting — not absence of signal.

| Subject | train CE (raw) | train CE (clean) | final-tick acc | verdict |
| --- | --- | --- | --- | --- |
| S01 | 1.52 | 1.22 | 59% | learns |
| S02 | 1.46 | 1.13 | 72% | learns |
| S03 | 1.40 | 1.13 | 68% | learns |
| S04 | 1.34 | 0.93 | 78% | learns |
| S05 | 1.36 | 0.94 | 76% | learns |
| S07 | 1.56 | 1.31 | 60% | learns |

Chance is 2.079 for cross-entropy and 12.5% for accuracy. Training loss falls smoothly and far below chance for every subject, validation tracks it closely (mild overfitting only on S07), and cleaning lowers cross-entropy by 0.24–0.35 across the board.

Figure 1. Per-subject learning curves on the cleaned data. Top row: per-tick cross-entropy (solid = train, dashed = validation, dotted = chance = ln 8 = 2.079). Bottom row: final-tick target accuracy (dotted = chance = 12.5%). Blue = cleaned inputs, red = raw. Training loss falls well below chance for every subject and validation tracks it.

Conclusion. The LSTM is functionally sound and there is learnable target information in the trajectory alone. The precondition set at the meeting is met. The earlier conclusion that ~87% of the decoder's wrong trials carry no recoverable intent was drawn from the copilot's open-loop endpoint conversion with accuracy-based epoch selection — it never measured whether the classifier learns, and it was measured on the corrupted trial set described in §3.

One nuance worth noting: cleaning sharply improves cross-entropy but barely moves final-tick accuracy. It is sharpening the model's belief and calibration, particularly early in the trial, more than it is changing the final argmax. That matters because the copilot integrates corrective velocity over all ticks, so earlier, better-calibrated belief should help even when final-tick accuracy is flat — which is what §6 finds.

# 5. Feature-space tuning

With the model shown sound, the third item asks which trajectory information carries the signal. Six feature configurations were trained on cleaned data, six subjects, three seeds each. The per-seed standard deviation is ±0.023, which is the key to reading the table.

| Configuration | features | val CE | val acc | reading |
| --- | --- | --- | --- | --- |
| basic + heading-consistency | 7 | 1.132 | 66.7% | ties basic |
| basic (current production) | 5 | 1.136 | 66.5% | — |
| basic + time + radius | 7 | 1.136 | 66.6% | ties basic |
| velocity only | 3 | 1.145 | 66.2% | ties basic |
| position + unit velocity | 4 | 1.158 | 66.8% | ~1 SD worse |
| position only | 2 | 1.285 | 62.9% | clearly worst |

The current feature set is already near-optimal. Every richer set — timing, radius, directional consistency — improves cross-entropy by less than the seed noise. Feature engineering is not where the remaining gain is. This is a useful negative result and it closes the item.

Velocity carries the target signal; position does not. Position-only is roughly six standard deviations worse than anything containing velocity, while velocity-only matches the full feature set within noise. The decodable target information is in the decoder's per-tick velocity — yet the task metric scores the accumulated endpoint position. The copilot's job is precisely to convert velocity-borne belief into endpoint position.

# 6. Does cleaning move the copilot's open-loop gain?

The end-to-end test: the full pipeline — held-out session blocks, per-subject on-policy training, open-loop evaluation — run twice with an identical control law, changing only whether the input trajectories are cleaned. Three seeds. Because cleaning is metric-safe, the raw-decoder baseline is identical across variants by construction, so any change in the gain is attributable to the copilot reading cleaner inputs.

| Variant | raw decoder | copilot | gain (copilot − decoder) |
| --- | --- | --- | --- |
| raw inputs | 62.73% | 63.83% | +1.10 ± 0.30 pp |
| cleaned inputs | 62.73% | 64.23% | +1.50 ± 0.13 pp |

Cleaning raises the gain by +0.40 pp and halves its across-seed variance. The raw-input figure of +1.10 pp reproduces the historically reported "+1 pp", now on the corrected trial set. (The 62.73% baseline here is over held-out test blocks only; the 64.0% in §3 is over all trials.)

Per subject, gain in percentage points, averaged over seeds:

| Subject | raw decoder acc | gain (raw inputs) | gain (cleaned inputs) | change |
| --- | --- | --- | --- | --- |
| S02 | 72.8% | +2.8 | +5.3 | +2.5 |
| S03 | 59.9% | −0.5 | +0.6 | +1.1 |
| S05 | 65.3% | +2.2 | +2.7 | +0.5 |
| S04 | 68.2% | +1.0 | +1.1 | +0.1 |
| S01 | 56.2% | +0.5 | −0.4 | −0.9 |
| S07 | 53.5% | −0.3 | −0.7 | −0.4 |

Cleaning helps the four subjects that already carry signal and is slightly negative on the two weakest (S01, S07, both near 53–56% raw accuracy). The net is positive with lower variance.

Honest reading. The effect is real but modest — +0.40 pp is roughly one standard deviation of the raw-input measurement. What makes it credible is the halved variance, the consistent direction across the signal-carrying subjects, and the S02 result (+2.8 → +5.3). It is not a step change. The additive open-loop control law still has limited headroom.

# 7. Status of the earlier conclusions

Because §3 invalidates the measurements behind the recent reports, the standing conclusions need to be sorted by what is now supported:

| Prior conclusion | Status |
| --- | --- |
| "No recoverable pattern / ~87% uncorrectable ceiling" | Refuted. The model demonstrably learns (§4); the ceiling was a diagnostics artifact and was measured on corrupted data. |
| Open-loop copilot gain ≈ +1 pp | Reproduced on the corrected data (+1.10 pp), and improved to +1.50 pp with cleaning. |
| Raw-decoder baseline ≈ 53–55% | Superseded. The correct figure is 64.0%. |
| Training-data composition study (sim blend ≈ +0.9 pp) | Not re-checked. Computed on the corrupted set; needs re-running. |
| Arm phase is saturated; language is the lever (7/22) | Not re-checked. Its arm-phase probes used the corrupted set and the superseded baseline. |

To be explicit about scope: only the clean-versus-raw comparison in §6 has been re-run on the fixed loader. The blend study, the ceiling diagnostic, and the 7/22 probes have not been, and their numbers should not be quoted until they are.

# 8. Recommendation and next steps

- First, and blocking — re-establish the baselines. re-run the training-data composition study, the ceiling diagnostic, and the 7/22 arm-phase probes on the fixed loader. Until this is done we do not know which of the last month's conclusions survive. The corrected baseline of 64.0% in particular changes the denominator for every "how much headroom is left" argument.

- Adopt the cleaned inputs. cleaning is metric-safe, improves the gain, and halves its variance. It should become the default input path for all subsequent work.

- Then revisit the direction question. the precondition set on 7/27 is met — the model does something useful from trajectory alone. Whether that justifies the closed-loop and language-prior directions is a judgement to make against re-established baselines, not against the current ones.

- Do not spend more effort on features. feature-space tuning is closed (§5) — the current set is already near-optimal, and no reasonable extension beat it. Effort here has low expected value.

Question for discussion. Given that the target signal is carried by velocity while the metric scores endpoint position (§5), is the fixed-length endpoint metric the right objective for the arm phase? This is a sharper, evidence-backed version of the metric question raised on 7/22.

# 9. Reproducibility

All three diagnostics are committed and run from the current data. The cleaning and loader fix live in the shared data module and are covered by the metric-safety and leakage checks described above.

| File | What it produces |
| --- | --- |
| diagnose_learning.py | §4 — train/validation loss curves; the model-soundness verdict and Figure 1 |
| feature_sweep.py | §5 — feature-configuration comparison |
| experiment_clean.py | §6 — clean vs raw copilot A/B, end to end |
| copilot_dataset.py | §2–3 — session-aware loading, the loader fix, and the cleaning functions |

Cleaning is opt-in via a flag, so raw-input runs remain reproducible for comparison. The loader fix is not optional — the previous behavior produced corrupted trials, so earlier runs will no longer reproduce their original numbers, by design.